## Sheet1
Keep track of the iterations of the program, as well as the features of that iteration.
~10 iterations is more than enough for coursework
Consider making iterations of features separately (e.g. player developed separate to enemy waves, then combine them together into 1 program)
Features of the iteration
Iteration No | Iteration Derived From | Changes | Bugs | Arena File Reading | File Cache | Platforms filled with sprites | Running (Player) | Wall Sliding (Player) | Collision Detection (Can't move into a platform) | Dashing (Player) | Player Animations | Thin Platforms | Dash Fade (Player) | Wall Jumping | Wall Jump Dash | Complete Arena Layout | Hurtbox Clipping Prevention
0.0.1 | N/A |  | Platform textures are stretched
0.0.2 (ITERATION 1) | 0.0.1 |  | When sliding down the wall, won't land on the ground
0.0.3 | 0.0.2 |  | Dashing lasts forever when in a wall, Dashing momentum will stop midair. (because dashing is distance based not time based) Wall collisions on thin platforms
0.0.4 | 0.0.3 |  | Dash Fade tries to generate when the player jumps and dashes almost simultaneously
0.0.5 | 0.0.4 |  | Low frame rate causing occasional platform clipping. Finishing dash in left wall of platform causes clip.
0.1.0 (ITERATION 2) | 0.0.5 | . Collision revamped to be ray based . New hurtbox updating algorithm. | The second line of pixels down in the middle of a thin platform is invisible sometimes, due to being between pixels
Features of the iteration
Iteration No | Iteration Derived From | Changes and Bug Fixes | Bugs | Ball Enemy | Enemy Spawning | Wave System | Player Attacks | Hitbox Collision | Main Class | Game Class | Camera | Player Attack Animations | Main Menu | Save file | Invinsibility frames | HUD | Sound Effects
0.1.1 | 0.1.0 | . Wall jump animation now uses frames 2, 3, 4. 1 and 5 cut from sprite sheet . Keybinds are taken from the main class by the player class. (Used to be called from the entity class but this would cause a compile loop due to #include looping from main to entity to main, etc) | . Doesn't run the game. Problem with creating new game objects and the MainLoop() | . No AI . Can't spawn yet . No projectile spawning | . Haven't tested | . Just loads into an array |  |  |  | . Incomplete Update() . No load/unload functions |  | . Untested . All functions except GrdSide
0.1.2 | 0.1.1 | . Number of waves reduced to 10 . Game object is now static, can load and unload properly. . Main object no longer handles creating the game instance, just directs the code to the game. | . Ball gets stuck when moving around corners to the player | . No projectiles . Incomplete AI |  | . Not fully tested | [5 empty] | . Unchanged | . Works . No button highlighting
0.2.0 (ITERATION 3) | 0.1.2 | . Upward velocity from a wall jump is applied when the first wall jump frame instead of wall slide frame (fixes wall jumping down when wall jumping before the wall slide frame is drawn) . Game object no longer uses _player, just takes the player directly from the entity manager (prevents player from dying over and over when respawning) . Ball now uses a gold sprite instead of silver . Ball now uses trig to find the velocities in the direction of the player. . Ball can maneuver around platforms based on the side of the platform and relative player position. . Added hitsounds, menu button sounds, victory and game over sounds | . GrdSide leg animation is slower than running animation |  |  |  | . Missing dash attack and charged attack | [5 empty] | . Unchanged